## Summary
openPCIE Root Complex — Tier 1 Verification Tracker
Document | TP-OPENPCIE-T1 (tracking workbook)
Version | 1.0
Date | 2026-10-20
DUT | riscv_pcie_soc (openPCIE 6e48e11, rtl/openPCIE)
Plans | docs/verification_plan.md, docs/testplan.md
Simulator | Vivado 2026.1 xsim
Metric | Value
Requirements
P1 requirements
Verified
Fail (expected, traced to a finding)
Partial / Open / Not run
Requirements covered by a test
Test cases
Passing with fixes
Passing on RTL as written
Regression runs
Pass rate, RTL as written
Pass rate, with fixes
Functional coverage (weighted)
Assertion cover points hit (not collected on xsim)
Open findings
How to use this workbook
Cells with a light-yellow fill are inputs: statuses, results, coverage hits, owners and comments. Everything else is reference data or a formula. |  | Input cell
Status columns use drop-down lists; the Summary sheet recalculates from them.
Example: after a nightly run, enter the pass counts in Regression!D and F and the assertion cover hits in Coverage!C; the Summary updates.
Requirement IDs match docs/verification_plan.md §6, and test IDs match docs/testplan.md §4.

## Features
Req ID | Requirement | Priority | RTL / spec reference | Check mechanism | Coverage item | Test case(s) | Status | Notes
SMOKE-001 | Firmware boots, mailbox handshake completes, one TLP traverses TX | P1 | — | Boot magic; scoreboard | — | TC-01 | Verified
TX-FMT-001 | 3-DW header + 1 payload DW → 2 beats, final tkeep=0xFF | P1 | riscv_pcie_soc.sv:195-211 | Predictor/scoreboard; SOC-003 | x_fmt_keep.ok_data_full | TC-01, TC-02, TC-03 | Verified
TX-FMT-002 | 3-DW header, no payload (Fmt[1]=0) → final tkeep=0x0F | P1 | :204 | Predictor/scoreboard; SOC-003 | x_fmt_keep.ok_nodata_partial | TC-02, TC-03 | Verified
TX-FMT-003 | First beat always tkeep=0xFF, tlast=0 | P1 | :197-199 | SOC-004, SOC-002 | cg_packet_t1 | All TX tests | Verified
TX-DATA-001 | Beat 0 = {HDR1,HDR0}, beat 1 = {DATA,HDR2}; no bit stuck, swapped or dropped | P1 | :196,203 | Scoreboard | — | TC-02 | Verified
TX-RAND-001 | All Tier 1 TLP kinds (MEM, IO, CFG0, CFG1, CPL) and Lengths 1–1024 framed correctly | P1 | :195-211 | Scoreboard | cg_tlp.cp_type, cp_len, x_type_fmt | TC-03 | Verified
TX-TRIG-001 | Only a write to TX_DATA starts a transmit; header writes are inert | P1 | :180-185 | Predictor; build_fw.py model | — | TC-08 | Verified
TX-TRIG-002 | Header registers are sticky across transmits | P2 | :177-179 | Scoreboard | — | TC-08 | Verified
TX-PROTO-001 | tvalid held until tready | P1 | AXI4-Stream §2.2.1 | AXIS-001 | c_stall* | All TX tests | Verified
TX-PROTO-002 | Payload stable while stalled | P1 | AXI4-Stream §2.2.1 | AXIS-002, monitor | c_stall_on_first/last | TC-04, TC-05, TC-06, TC-11 | Verified
TX-PROTO-003 | tkeep contiguous; partial only on tlast | P1 | AXI4-Stream Table 2-2 | AXIS-004/005 | cg_packet_t1 | All TX tests | Verified
TX-PROTO-004 | Transmit survives backpressure without losing a beat | P1 | :200,208 | AXIS-002 + scoreboard | c_tx_stall_in_c1/c2 | TC-04, TC-05, TC-06, TC-11 | Fail (expected) | Fails on RTL as written; passes with fix 0002 (finding TX-PROTO-004)
TX-FLOW-001 | Behaviour with tx_buf_av = 0 documented (DUT does not gate on credits) | P3 | :153 | Directed readback | c_tx_while_no_credit, cp_tx_buf_av.empty | TC-09 | Verified
TX-FLOW-002 | Software must poll tx_state==IDLE before each send (no HW interlock) | P3 | :180-185 | Documented contract | — | — | Verified | Documented software contract; no test
RX-CAP-001 | Completion status captured from tdata[47:45] | P1 | :217-219 | Readback vs predictor | cg_reg_access | TC-07 | Verified
RX-CAP-002 | Phase 1 captures DW2 → RX_HDR_INFO, DW3 → RX_DATA | P1 | :223-224 | Readback vs predictor | cg_reg_access | TC-07 | Verified
RX-CAP-003 | A non-completion inbound TLP leaves capture registers unchanged | P2 | :217 | Predictor mirrors RTL | — | TC-07 | Verified
RX-CAP-004 | m_axis_rx_tready is tied high | P2 | :233 | SOC-006 | — | All | Verified
REG-001 | All five readable registers decode correctly | P1 | :243-249 | RAL + scoreboard | x_offset_dir | TC-08 | Verified
REG-002 | TX registers are write-only; reads return 0 | P1 | :248 | Directed check | x_offset_dir | TC-08 | Verified
REG-003 | Read decode aliases every 64 bytes | P3 | :239-249 | Directed alias check | cp_offset.aliased | TC-08 | Verified
REG-004 | A write to a read-only register has no side effect | P2 | :175 | Scoreboard packet compare | x_offset_dir | TC-08 | Fail (expected) | Alias confirmed on RTL as written; fixed by patch 0003
CFG-001 | ERR_STATUS = {err_fatal, cfg_status} | P1 | :152 | Readback vs predictor | cg_sideband | TC-09 | Verified
CFG-002 | PHY_STATUS[5:0] tracks tx_buf_av | P1 | :153 | Readback (masked) | cp_tx_buf_av | TC-09 | Verified
CFG-003 | cfg_command has no effect (port unused) | P3 | :60 | SOC-010 | — | TC-09 | Verified
RST-001 | Reset clears the RX capture registers and the TX FSM | P1 | :157-167 | Directed readback | — | TC-10 | Verified
RST-002 | CPU re-boots and the datapath works after reset | P1 | — | Re-boot handshake + traffic | — | TC-10 | Verified
CPU-001 | PicoRV32 bus handshake is honoured by the bridge | P2 | :172-173,256 | SOC-008/009/011 | — | All | Verified
MIX-001 | Sustained mixed traffic under random backpressure | P1 | — | Full environment | All groups | TC-11 | Verified

## Test Cases
TC ID | UVM test | Virtual sequence | Type | Priority | Sink profile / config | Timeout | Requirements | Stimulus | Checks / expected result | Result: RTL as written | Result: with fixes | Owner | Comments
TC-01 | openpcie_smoke_test | openpcie_smoke_vseq | D | P1 | READY_ALWAYS | 2 ms | SMOKE-001, TX-FMT-001 | Boot; one MemWr32 @0x1000_0000 (0xCAFE_BABE); sync; read PHY_STATUS, ERR_STATUS | 2-beat packet matched (final tkeep 0xFF); readbacks match predictor; SVA clean | Pass | Pass
TC-02 | openpcie_tx_directed_test | openpcie_tx_directed_vseq | D | P1 | READY_ALWAYS | 10 ms | TX-FMT-001/002/003, TX-DATA-001 | 3 MemWr32 (zero, all-ones, mixed); 2 MemRd32; 1 CplD; 32 MemWr32 walking-ones payload | 38 packets matched; tkeep 0xFF with payload, 0x0F without; SOC-003/004 | Pass | Pass
TC-03 | openpcie_tx_random_test | openpcie_tx_random_vseq | CR | P1 | READY_ALWAYS | 20 ms | TX-RAND-001, TX-FMT-001/002/003 | 20–400 random TLPs: Fmt with/without data; MEM/IO/CFG0/CFG1/CPL; MEM reads Length 1–1024 | Scoreboard packet compare; SVA | Pass | Pass
TC-04 | openpcie_tx_backpressure_test | openpcie_tx_backpressure_vseq | D/CR | P1 | READY_RANDOM, 40 % | 20 ms | TX-PROTO-001/002/004 | 30–200 TLPs alternating MemWr32 / MemRd32 under random stalls | AXIS-001/002, monitor stability, scoreboard; responder confirms stalls | Fail (expected) | Pass
TC-05 | openpcie_tx_slow_sink_test | openpcie_tx_backpressure_vseq | D | P1 | READY_SLOW, period 4 | 20 ms | TX-PROTO-001/002/004 | As TC-04, one beat accepted every 4 cycles | As TC-04 | Fail (expected) | Pass
TC-06 | openpcie_tx_burst_sink_test | openpcie_tx_backpressure_vseq | D | P1 | READY_BURST, 1 accept / 3 stall | 20 ms | TX-PROTO-001/002/004 | As TC-04, alternating accept/stall runs | As TC-04 | Fail (expected) | Pass
TC-07 | openpcie_rx_cpl_test | openpcie_rx_cpl_vseq | D/CR | P1 | READY_ALWAYS; no TX required | 20 ms | RX-CAP-001/002/003 | 10–100 CplD cycling SC/UR/CRS/CA + readback of RX_STATUS/RX_DATA/RX_HDR_INFO; 4 Cpl without data; 1 inbound MemWr32 | Readbacks equal predictor shadow; RX_DATA unchanged after non-Cpl TLP | Pass | Pass
TC-08 | openpcie_reg_access_test | openpcie_reg_access_vseq | D | P1 | READY_ALWAYS; RAL built | 10 ms | REG-001..004, TX-TRIG-001/002 | RAL read 5 RO regs; write TX_HDR0..2; read back WO regs; write all RO regs (MRd header to +0x20); RAL read again; write TX_DATA; read +0x14 vs +0x54 | WO reads 0; RO unchanged; packet = MRd (RTL as written) or MWr (fixed), predictor matches both; +0x54 aliases +0x14 | Pass | Pass
TC-09 | openpcie_sideband_test | openpcie_sideband_vseq | D | P1 | READY_ALWAYS | 20 ms | CFG-001/002/003, TX-FLOW-001 | tx_buf_av 32→0 with cfg_status 0/FFFF/0010, TLP + PHY_STATUS read each step; err_fatal with cfg_status A5A5; err_fatal at credits 16..0 | PHY_STATUS[5:0] = tx_buf_av; ERR_STATUS = {err_fatal, cfg_status}; TX continues at 0 credits; SOC-010 | Pass | Pass
TC-10 | openpcie_reset_test | openpcie_reset_vseq | D | P1 | READY_ALWAYS | 20 ms | RST-001/002 | 8 MemWr32; reset pulse 20 cycles; wait re-boot; read RX_DATA, RX_STATUS; 8 MemWr32 | Firmware re-boots; RX regs read 0; post-reset packets match | Pass | Pass
TC-11 | openpcie_random_test | openpcie_random_vseq | CR | P1 | READY_RANDOM, 65 % | 60 ms | MIX-001, TX-PROTO-004, all groups | 50–500 iterations: MemWr32 40 %, MemRd32 20 %, CplD out 10 %, CplD in 10 %, reg read 10 %, sideband change 10 % | Full environment: scoreboard, predictor, monitor, all SVA | Fail (expected) | Pass

## Traceability
Req ID | Priority | TC-01 | TC-02 | TC-03 | TC-04 | TC-05 | TC-06 | TC-07 | TC-08 | TC-09 | TC-10 | TC-11 | Primary tests | Total tests | Covered?
SMOKE-001 | P1 | bar: TC-01
TX-FMT-001 | P1 | bar: TC-01 to TC-06; TC-08 to TC-11
TX-FMT-002 | P1 | bar: TC-02 to TC-06; TC-08; TC-11
TX-FMT-003 | P1 | bar: TC-01 to TC-06; TC-08 to TC-11
TX-DATA-001 | P1 | bar: TC-02 to TC-03; TC-11
TX-RAND-001 | P1 | bar: TC-03; TC-11
TX-TRIG-001 | P1 | bar: TC-08
TX-TRIG-002 | P2 | bar: TC-08
TX-PROTO-001 | P1 | bar: TC-01 to TC-06; TC-08 to TC-11
TX-PROTO-002 | P1 | bar: TC-04 to TC-06; TC-11
TX-PROTO-003 | P1 | bar: TC-01 to TC-11
TX-PROTO-004 | P1 | bar: TC-04 to TC-06; TC-11
TX-FLOW-001 | P3 | bar: TC-09
TX-FLOW-002 | P3
RX-CAP-001 | P1 | bar: TC-07; TC-11
RX-CAP-002 | P1 | bar: TC-07; TC-11
RX-CAP-003 | P2 | bar: TC-07
RX-CAP-004 | P2 | bar: TC-01 to TC-11
REG-001 | P1 | bar: TC-01; TC-06 to TC-11
REG-002 | P1 | bar: TC-08
REG-003 | P3 | bar: TC-08
REG-004 | P2 | bar: TC-08
CFG-001 | P1 | bar: TC-01; TC-08 to TC-09; TC-11
CFG-002 | P1 | bar: TC-01; TC-08 to TC-09
CFG-003 | P3 | bar: TC-09; TC-11
RST-001 | P1 | bar: TC-10
RST-002 | P1 | bar: TC-10
CPU-001 | P2 | bar: TC-01 to TC-11
MIX-001 | P1 | bar: TC-11
● primary target of the test ○ also exercised and checked
Requirements per test (primary):
Requirements per test (any):

## Coverage
Functional coverage — Vivado 2026.1 xsim, merged over 55 runs on fixed RTL
Covergroup | Coverpoints / crosses | Weight | Goal | 2026-09-26 | Latest | Status | Source
cg_reg_access | offset (9 named + aliased), direction, offset × direction | 1 | 100% | 85.2% | 100% |  | openpcie_soc_coverage.svh
cg_tlp | Type, Fmt, Length, final tkeep, Fmt × tkeep, Type × Fmt | 1 | 100% | 61.5% | 100% |  | openpcie_soc_coverage.svh
cg_sideband | tx_buf_av, err_fatal, cfg_status, credit × err_fatal | 1 | 100% | 56.3% | 100% |  | openpcie_soc_coverage.svh
cg_packet_t1 (tx, rx) | 2 beats; final tkeep 0x0F/0xFF; 12/16 bytes | 1 | 100% | — | 100% |  | openpcie_axis_coverage.svh
cg_packet (tx, rx) | All packet shapes (kept for Tier 2) | 0 | n/a | 24.1% | 24.1% |  | openpcie_axis_coverage.svh
cg_tlp_diag | Non-conforming Fmt/tkeep pairs — must stay empty | 0 | n/a | — | 0% |  | openpcie_soc_coverage.svh
Weighted score (weight-1 groups)
Note: cg_tlp_diag at 0 % is the passing outcome. The 2026-09-26 column is the pre-closure baseline (merged score 55.6 %). Sign-off goal: ≥ 95 %.
Assertion cover points (need VCS or Xcelium; xsim ignores cover property)
Cover point | Source | Hits | Status
c_stall | openpcie_axis_sva.sv
c_stall_2cyc | openpcie_axis_sva.sv
c_stall_5cyc | openpcie_axis_sva.sv
c_stall_on_first | openpcie_axis_sva.sv
c_stall_on_last | openpcie_axis_sva.sv
c_btb_packets | openpcie_axis_sva.sv
c_partial_last | openpcie_axis_sva.sv
c_full_last | openpcie_axis_sva.sv
c_tx_full_packet | openpcie_soc_sva.sv
c_tx_stall_in_c1 | openpcie_soc_sva.sv
c_tx_stall_in_c2 | openpcie_soc_sva.sv
c_rx_phase_toggle | openpcie_soc_sva.sv
c_credit_exhausted | openpcie_soc_sva.sv
c_tx_while_no_credit | openpcie_soc_sva.sv

## Checkers
ID | Source | Property / check | Requirement(s) | Kind | RTL as written | With fixes
AXIS-001 | openpcie_axis_sva.sv | tvalid stays high until tready | TX-PROTO-001 | Assertion | Fires (TX-PROTO-004) | Clean
AXIS-002 | openpcie_axis_sva.sv | tdata/tkeep/tlast stable while stalled | TX-PROTO-002, TX-PROTO-004 | Assertion | Fires (TX-PROTO-004) | Clean
AXIS-003 | openpcie_axis_sva.sv | A valid beat carries at least one byte | TX-PROTO-003 | Assertion | Clean | Clean
AXIS-004 | openpcie_axis_sva.sv | tkeep contiguous from bit 0 | TX-PROTO-003 | Assertion | Clean | Clean
AXIS-005 | openpcie_axis_sva.sv | Only the last beat may be partial | TX-PROTO-003 | Assertion | Clean | Clean
AXIS-006 | openpcie_axis_sva.sv | No X/Z on control or data while tvalid | TX-PROTO-003 | Assertion | Clean | Clean
AXIS-007 | openpcie_axis_sva.sv | tvalid/tready never X out of reset | TX-PROTO-001 | Assertion | Clean | Clean
SOC-001 | openpcie_soc_sva.sv | tx_state only takes legal encodings | TX-FMT-003 | Assertion | Clean | Clean
SOC-002 | openpcie_soc_sva.sv | A packet is exactly two beats | TX-FMT-003 | Assertion | Fires (TX-PROTO-004) | Clean
SOC-003 | openpcie_soc_sva.sv | Final tkeep ∈ {0x0F, 0xFF} and agrees with Fmt[1] | TX-FMT-001, TX-FMT-002 | Assertion | Clean | Clean
SOC-004 | openpcie_soc_sva.sv | First beat tkeep = 0xFF | TX-FMT-003 | Assertion | Clean | Clean
SOC-005 | openpcie_soc_sva.sv | No tvalid while tx_state == IDLE | TX-FMT-003 | Assertion | Clean | Clean
SOC-006 | openpcie_soc_sva.sv | m_axis_rx_tready tied high | RX-CAP-004 | Assertion | Clean | Clean
SOC-007 | openpcie_soc_sva.sv | rx_phase never X/Z | RX-CAP-002 | Assertion | Clean | Clean
SOC-008 | openpcie_soc_sva.sv | CPU request stable until mem_ready | CPU-001 | Assertion | Clean | Clean
SOC-009 | openpcie_soc_sva.sv | mem_ready traceable to a request this or last cycle | CPU-001 | Assertion | Clean | Clean
SOC-010 | openpcie_soc_sva.sv | cfg_command, cfg_status, tx_buf_av never X/Z | CFG-003 | Assertion | Clean | Clean
SOC-011 | openpcie_soc_sva.sv | Trailing mem_ready pulse lasts at most one cycle | CPU-001 | Assertion | Clean | Clean
SCBD/TX | openpcie_scoreboard.svh | Observed TX packet equals predicted; no unexpected/missing packets | TX-* | Checker | Fires (TX-PROTO-004) | Clean
SCBD/RD | openpcie_scoreboard.svh | Register readback equals predictor shadow | REG-*, RX-CAP-*, CFG-* | Checker | Clean | Clean
SCBD (EOT) | openpcie_scoreboard.svh | No leftovers; TX activity seen when required | All | Checker | Clean | Clean
AXIS/PROTO | openpcie_axis_monitor.svh | Handshake/stability rules needing packet history | TX-PROTO-* | Checker | Fires (TX-PROTO-004) | Clean
FWBOX | openpcie_fw_mailbox.svh | Boot timeout, command timeout, mailbox handshake order | SMOKE-001 | Checker | Clean | Clean

## Findings
ID | Severity | Description | Location | Found by | Evidence | Fix | Status | Upstream issue / PR | Comments
TX-PROTO-004 | High | TX FSM samples tready one cycle early; beat 0 is lost under backpressure | riscv_pcie_soc.sv:195-211 | TC-04, TC-05, TC-06, TC-11 | Confirmed | patches/0002-tx-fsm-honour-axis-handshake.patch | Open
REG-004 | Medium | Register writes ignore addr[5]: write to PHY_STATUS overwrites TX_HDR0; write to +0x2C starts a transmit | :175 | TC-08 | Confirmed | patches/0003-bridge-write-decode-use-addr5.patch | Open
RTL-SIM-001 | Medium | ram written by both $readmemh and always_ff; VCS will not elaborate | :99-120 | all (compile) | Confirmed | patches/0001-ram-always-instead-of-always_ff.patch (applied by patch layer) | Open
CFG-003 | Low | cfg_command input never read; unconnected at chip top | :60 | TC-09 | Documented | — | Open
RTL-SIM-002 | Low | RAM path re-arms mem_ready for one extra cycle (benign) | :106-120 | SOC-009/011 | Documented | Optional: && !ram_ready_reg | Open
TX-FLOW-002 | Info | No HW busy interlock on TX_DATA; software must poll tx_state | :180-185 | — | Documented | — | Closed
REG-003 | Info | Read decode aliases every 64 bytes | :239-249 | TC-08 | Documented | — | Closed
RX-CAP-003 | Info | RX capture FSM cannot resynchronise to packet boundaries | :215-229 | TC-07 | Documented | — | Closed
FW-001 | Info | Initial stack pointer 0x2000 is one word past the RAM (latent) | tb/fw/mailbox_fw.s | — | Documented | — | Closed

## Regression
Regression results — Vivado 2026.1 xsim, seeds 1–5, 2026-10-20
TC ID | Test | Seeds | Pass: RTL as written | Fail: RTL as written | Pass: with fixes | Fail: with fixes | Verdict
TC-01 | openpcie_smoke_test | 5 | 5 |  | 5
TC-02 | openpcie_tx_directed_test | 5 | 5 |  | 5
TC-03 | openpcie_tx_random_test | 5 | 5 |  | 5
TC-04 | openpcie_tx_backpressure_test | 5 | 0 |  | 5
TC-05 | openpcie_tx_slow_sink_test | 5 | 0 |  | 5
TC-06 | openpcie_tx_burst_sink_test | 5 | 0 |  | 5
TC-07 | openpcie_rx_cpl_test | 5 | 5 |  | 5
TC-08 | openpcie_reg_access_test | 5 | 5 |  | 5
TC-09 | openpcie_sideband_test | 5 | 5 |  | 5
TC-10 | openpcie_reset_test | 5 | 5 |  | 5
TC-11 | openpcie_random_test | 5 | 0 |  | 5
Total
Pass rate
Every failure on the RTL as written is AXIS/PROTO + SCBD/TX from TX-PROTO-004 (4163 errors in the 20 failing runs: 3447 AXIS/PROTO, 400 SVA/AXIS, 196 SVA/SOC, 120 SCBD/TX). Source: build/xsim/regress_nofix and regress_fixed logs.